## Sheet1
Unadjusted Use Case Weight
Use case complexity | Weight | Number of use cases | Product
Simple | 5 | 1 | 5
Average | 10 | 1 | 10
Complex | 15 | 2 | 30
Total |  | UUCW: | 45
Unadjusted Actor Weight
Actor Type | Weight | Number of Actors | Product | Notes
Simple | 1 | 0 | 0
Average | 2 | 1 | 2 | Database
Complex | 3 | 1 | 3 | Opponent
Total |  | UAW: | 5
Unadjusted Use Case Points |  | UUCP: | 50
Technical Complexity Factor |  | Scale 0 to 5
Factor | Weight | Assessment | Impact
Distributed system | 2 | 1 | 2
Performance objectives | 2 | 0 | 0
End-user efficiency | 1 | 0 | 0
Complex processing | 1 | 0 | 0
Reusable code | 1 | 0 | 0
Easy to install | 0.5 | 0 | 0
Easy to use | 0.5 | 3 | 1.5
Portable | 2 | 0 | 0
Easy to change | 1 | 0 | 0
Concurrent use | 1 | 0 | 0
Security | 1 | 0 | 0
Access for third parties | 1 | 0 | 0
Training needs | 1 | 0 | 0
Total |  | TFactor: | 3.5
|  | TCF: | 0.635
Environmental Factor |  | Scale 0 to 5
Factor | Weight | Assessment | Impact
Familiar with the development process | 1.5 | 4 | 6
Application experience | 0.5 | 4 | 2
Object-oriented experience | 1 | 3 | 3
Lead analyst capability | 0.5 | 4 | 2
Motivation | 1 | 5 | 5
Stable requirements | 2 | 5 | 10
Part-time staff | -1 | 5 | -5
Difficult programming language | -1 | 5 | -5
Total |  | EFactor: | 18
|  | EF: | 0.86
Use Case Point Total |  | UCP: | 27.305
Project Duration Estimation
Number of developers | 2
Developer hours per weekday | 2
Developer hours per weekend | 8
Total developer hours per week | 22
Hours per UCP |  | Hours | Weeks
Min | 20 | 546.1 | 12.4114
Max | 28 | 764.54 | 17.3759